Weekly Report for MSc Project

| Student RGU ID: | 2425488 |
| --- | --- |
| Student IIT ID: | 20241504 |
| Student name | Hiran Abeywardhana |
| Course | MSc Big Data Analytics |
| Module | CMM799 MSc Project |
| Project Topic | Cross-Domain Machine Learning Framework for Scalable GUI Element Detection and Adaptation in Desktop Environments |
| Supervisor | Mr.Pumudu Fernando |
| Week commencing on dd / mmm / yyyy | 19/05/2026 |
| Meeting with the supervisor | Yes |
|  | Met the supervisor on Tuesday. Presented the four-method TSR and the Phase 1 evidence bundle. Supervisor asked me to make sure the '22-fold' auto-label mAP inflation is documented as a real risk that was mitigated, not swept under the rug. |
| Description of progress this week | I met the supervisor on Tuesday and presented two things: the four-method TSR (template 46.7, ocr-only 33.3, pywinauto 6.7, VisClick 73.3) and the Phase 1 evidence bundle. The hardware spec (Windows 11 Enterprise 22631, Intel Core Ultra 5 135H, 32 GB, Intel Arc iGPU, 1920x1080), the detector-only ONNX benchmark (median 67.81 ms, p95 79.02 ms over 50 runs), the peak RSS (212 MB detector-only, 764 MB after EasyOCR warm-up), and the R-FR / R-NFR requirements-evidence table. Supervisor asked me to be explicit in the report about the auto-label mAP inflation issue (the 22-fold overstatement I hit early on) so it reads as a mitigated risk rather than a hidden bug. I updated the risk register in the data form. |
| Plan for next week | Next week is Phase 4 kick-off. I plan to commit to the Phase 4 triple: DETR baseline, few-shot curve rerun with the newer protocol, and SSP+FT proper. UDA is a stretch goal. |
| Date of report | 26/05/2026 |
| Student Photo Signature |  |

To be submitted to the supervisor weekly, with the latest page on top.  Upload to the drop box on the relevant module pages on Campus Moodle when you are submitting your final report.